## Instructions
HOW TO USE THIS WORKBOOK
1. Release | The QA lead fills this sheet once per release (ID, name, date, builds, key risk, actions). Developers leave it alone.
2. Journeys (mandatory) | Each developer adds ONE ROW per journey per platform that they own: final counts, plus notes (blockers, reasons). Total must equal Passed + Failed + Blocked + Skipped.
3. Defects | One row per defect or issue. Fill Journey, Severity, Status, Owner, ETA, Jira URL, Failure Type and how many tests it affects. Severity counts and failure classification on the dashboard are calculated from this sheet.
Rules
Use the dropdowns - typed values that do not match are rejected by the build step.
Use the same Journey and Platform spelling on every sheet.
Never type percentages - they are calculated.
Blocked and Skipped scenarios count against the pass rate (pass rate = passed / total planned).
Several people can work in one shared file (SharePoint / OneDrive co-authoring), or each person can keep a separate copy - put all files in the input folder and the build step merges them.
To publish: node tools/build-data.js (updates data/regression.json, previous releases are kept).

## Release
Field | Value | Help
Release ID |  | e.g. 2026.10 - must be unique, used to replace/update this release
Release Name |  | e.g. October 2026 Release
Release Date |  | Regression sign-off / report date
iOS Build |  | e.g. 5.12.0 (2431)
iOS Devices |  | e.g. iPhone 15 (iOS 17.5), iPhone 12 (iOS 16.7)
Android Build |  | e.g. 5.12.0 (7120)
Android Devices |  | e.g. Pixel 8 (Android 14), Galaxy S22 (Android 13)
Decision Override |  | Optional (QA lead only): In Progress / Completed. Blank = calculated automatically
Decision Note |  | Optional: reason shown with the decision
Key Risk |  | Free text for leadership
Action 1 |  | Owner: action
Action 2 |  | Owner: action
Action 3 |  | Owner: action

## Journeys
Journey | Platform | Owner | Total Tests | Passed | Failed | Blocked | Skipped | Status (optional) | Notes | Check

## Defects
Defect ID | Title | Journey | Platform | Severity | Status | Owner | Reported | Target Fix / ETA | Jira URL | Failure Type | Affected Tests | Impact / Notes