## Instructions
HOW TO USE THIS WORKBOOK
1. Release | The QA lead fills this sheet once per release (ID, name, date, builds, key risk, actions). Developers leave it alone.
2. Journeys (mandatory) | Each developer adds ONE ROW per journey per platform that they own: final counts, plus notes (blockers, reasons). Total must equal Passed + Failed + Blocked + Skipped.
3. Defects | One row per defect or issue. Fill Journey, Severity, Status, Owner, ETA, Jira URL, Failure Type and how many tests it affects. Severity counts and failure classification on the dashboard are calculated from this sheet.
Rules
Use the dropdowns - typed values that do not match are rejected by the build step.
Use the same Journey and Platform spelling on every sheet.
Never type percentages - they are calculated.
Blocked and Skipped scenarios count against the pass rate (pass rate = passed / total planned).
Several people can work in one shared file (SharePoint / OneDrive co-authoring), or each person can keep a separate copy - put all files in the input folder and the build step merges them.
To publish: node tools/build-data.js (updates data/regression.json, previous releases are kept).

## Release
Field | Value | Help
Release ID | 2026.10 | e.g. 2026.10 - must be unique, used to replace/update this release
Release Name | October 2026 Release | e.g. October 2026 Release
Release Date | 2026-10-18 | Regression sign-off / report date
iOS Build | 5.12.0 (2431) | e.g. 5.12.0 (2431)
Android Build | 5.12.0 (7120) | e.g. 5.12.0 (7120)
Decision Override |  | Optional (QA lead only): In Progress / Completed. Blank = calculated automatically
Decision Note |  | Optional: reason shown with the decision
Key Risk | Regression is blocked on both platforms as envirnment is down | Free text for leadership
Action 1 | CIAM Team will update the team,once enviroment is up. QA to retest on both platforms | Owner: action
Action 2 | FE: Fix server not responding on login screen; QA to retest on both platforms | Owner: action
Action 3 | BE: confirm environment fix for eligibility API timeouts | Owner: action

## Journeys
Journey | Platform | Owner | Total Tests | Passed | Failed | Blocked | Skipped | Status (optional) | Notes | Check
Payments and Transfer | iOS | Waleed | 24 | 24 | 0 | 0 | 0 | Pass |  | OK
Open Finance | iOS | Nazim | 30 | 30 | 0 | 0 | 0 | Pass |  | OK
LVS | iOS | Althad | 28 | 27 | 1 | 0 | 0 | Fail | Environment was down | OK
DFVS | iOS | Gautam | 20 | 9 | 0 | 11 | 0 | Blocked | Test data dependency with PRIME | OK
Fraud | iOS | Abel | 35 | 35 | 0 | 0 | 0 | Pass |  | OK
Branch services | iOS | Bhustan | 22 | 19 | 3 | 0 | 0 | Fail | Script maintanance | OK
Minor | iOS | Nazim | 18 | 18 | 0 | 0 | 0 | Pass | Push permission test is flaky on iOS 17 simulator; passed on third pipeline. | OK
PFM | iOS | Sadiya | 16 | 16 | 0 | 0 | 0 | Pass |  | OK
Payments and Transfer | Android | Waleed | 24 | 24 | 0 | 0 | 0 | Pass |  | OK
Open Finance | Android | Nazim | 30 | 30 | 0 | 0 | 0 | Pass | Failures were device-farm network drops; cleared on re-run. | OK
LVS | Android | Althad | 28 | 28 | 0 | 0 | 0 | Pass |  | OK
DFVS | Android | Gautam | 20 | 9 | 0 | 11 | 0 | Blocked | Change requirement, script maintanance | OK
Fraud | Android | Abel | 35 | 35 | 0 | 0 | 0 | Pass |  | OK
Branch services | Android | Bhustan | 22 | 19 | 3 | 0 | 0 | Fail | server not responding | OK
Minor | Android | Nazim | 18 | 18 | 0 | 0 | 0 | Pass |  | OK
PFM | Android | Sadiya | 16 | 16 | 0 | 0 | 0 | Pass |  | OK

## Defects
Defect ID | Title | Journey | Platform | Severity | Status | Owner | Reported | Target Fix / ETA | Jira URL | Failure Type | Affected Tests | Impact / Notes
DEF-2041 | Environment was down | Payments and Transfer | Both | Critical | In Progress | Waleed | 2026-10-12 | 2026-10-22 | https://jira.example.com/browse/DEF-2041 | Application defect | 5 | Referral status changes in the app never reach the EHR; blocks referral sign-off on both platforms.
DEF-2043 | Test data dependency with PRIME | Open Finance | Both | High | Open | Nazim | 2026-10-14 | 2026-10-20 | https://jira.example.com/browse/DEF-2043 | Application defect | 22 | 11 scenarios per platform blocked until upstream change lands.
DEF-2047 | Server not responding on login | LVS | iOS | High | In Progress | Althaf | 2026-10-15 | 2026-10-19 | https://jira.example.com/browse/DEF-2047 | Environment / test data | 1 | Intermittent; retest scheduled before sign-off.